## Splash
Software Test Engineering
Test Strategy Development
Analysis Template
by
Craig Kam

## Intro
Introduction | This template is not a format for writing a test strategy document. Rather, it is designed to help the user determine what kinds of things should be considered in developing an overall strategy. This guide is designed to get the test engineer pointed in the right direction. The template is divided into tabs by discovery areas such as Scope or Analysis. Each tab has tasks related to that area. Each task has a grey box next to it. Select the box and enter your details. If there is a comment available, it will display. Once the discovery tasks have been completed, the user should have sufficient information to begin the formal strategy design. The template is very flexible. The basic discovery tasks listed can be easily modified or deleted depending on a specific company's needs. Where appropriate, comments with additional information and suggestions have been added. These comments can be noted by a red triangle in the upper right corner of a cell. Comments can be easily customized to reflect the particular requirements of the audience. For those unfamiliar with Excel, the text entry areas are set for word wrapping. The text areas are made up of merged cells and are not text boxes. The design of the template intends the user to keep writing in a serial manner. If however, the user needs to use a carriage return in the text box, the (Alt-Enter) combination can be used. Of course, this material can be ported to whatever application best suits the user's purpose.
Developing a coherent test strategy for a new software product or for major changes to an existing product can be challenging.
This is especially true for the new test engineer for whom this template was developed.
This template is a basic guide to help the user through the discovery thought processes necessary to create a sound test strategy for a project.
This template is not a format for writing a test strategy document. Rather, it is designed to help the user determine what kinds of things should
be considered in developing an overall strategy. This guide is designed to get the test engineer pointed in the right direction
The template is divided into tabs by discovery areas such as Scope or Analysis. Each tab has tasks related to that area.
Each task has a grey box next to it. Select the box and enter your details. If there is a comment available, it will display.
Once the discovery tasks have been completed, the user should have sufficient information to begin the formal strategy design.
The template is very flexible. The basic discovery tasks listed can be easily modified or deleted depending on a specific
company's needs.
Where appropriate, comments with additional information and suggestions have been added. These comments can be noted by a red
triangle in the upper right corner of a cell.
Comments can be easily customized to reflect the particular requirements of the audience.
For those unfamiliar with Excel, the text entry areas are set for word wrapping. The text areas are made up of merged cells and are not
text boxes.
The design of the template intends the user to keep writing in a serial manner. If however, the user needs to use a carriage return
in the text box, the (Alt-Enter) combination can be used.
Of course, this material can be ported to whatever application best suits the user's purpose.

## Table of Contents
Table of Contents
| 1 | Scope - 1
| 2 | Scope - 2
| 3 | Analysis/Research
| 4 | Assessment Steps
| 5 | Strategy Components - 1
| 6 | Strategy Components - 2
| 7 | Closing

## Scope 1
Task Name |  | Back to TOC
Specify Scope of Product Testing
List Scope Components
Types of Testing Required
Initial Time Frames
Reporting Requirements
Note on B3: Identify what is to be tested in this effort. This what your strategy will need to cover.
Note on B22: This will be a moving target. Start with what you know now.
Note on D6: Suggestions: 1. List all modules of the new application to be tested. 2. List all modules of the existing application that need to be tested. 3. List any integrated components that share inforamtion with items in 1 or 2. Determine if testing these 'integrated' items are within your strategy scope. 4. This can be a large area, ask for help if you are unsure.
Note on D14: Suggestions: 1. Smoke/Acceptance 2. Functional 3. Integration 4. Regression 5. Sysytem/E2E 6. Performance 7. Other Not all components may require the same types of testing. If this the case, specify this.
Note on D22: Suggestions: 1. Current Module Delivery Schedule - this can help set priorities. Your manager will know this. 2. Test Cycle Start and End Dates. 3. Delivery date of Test Plan Strategy Document. 4. Etc. 5. Keep a schedule handy all the time. You may get new schedules weekly.
Note on D30: Suggestions: 1. Strategy Plan Progress - What type,how often, and to whom. 2. Test Reporting (1) The strategy document should specify how and when test reporting will be delivered. For example, within 2 days of close of test cycle. 3. Test Reporting (2) Include specifics regarding what should be included in the test reports. Most shops have standards for items 2 and 3. Things like defect counts and fixes.

## Scope 2
Task Name |  | Back to TOC
Specify Scope of Product Testing (continued)
Resources/Persons
Resources/Hardware
Identify Stakeholders
Define Major Task Milestones
Note on B6: Who will be available to implement this strategy. Who will be doing the work.
Note on B14: What test environments will be needed to execute the test strategy.
Note on B22: List all the different individuals/departments that are concerned with the outcome of the project
Note on C30: Define the key components of your overall strategy. Define how you will measure your strategy development progress.
Note on E6: Suggestions: 1. You 2. Typically, all or some part of your test team 3. Vendors or partner staff (integration application staff). 4. Customers 5. Other stakeholders
Note on E14: Suggestions: 1. QA group test environment. 2. Development group(s) test environment. 3. Partner (integrated applications) environments. 4. Other Specify if different environments are required for individual components of testing.
Note on E22: Suggestions: (groups include both associates and their management) 1. Upper management 2. Your management 3. Peers 4. Business/marketing 5. Development 6. Customers 7. Business Analysis group 8. Integrated Partner Applicaion groups 9. Performance 10. Architecture 11. Vendors
Note on E30: Suggestions: 1. Document Review 2. Stakeholder Interviews 3. Determine scope 4. Identify potential strategies 5. Define timeframes for accomplishment of milestones. 6. Define initial test data needs (this will change over time). 7. Define test progress reporting requirements (type and frequency. 8. Define test cycle size and frequency and related deadlines. 9. Indicate if Post mortem reviews are required. 10. etc.

## Analysis_Research
Task Name |  |  | Back to TOC
Analysis/Research
Requirement Identification Steps
Suggestions_A:
Includes:
Documents
Flowcharts
Traceabilty matrix
Suggestions_B:
Includes:
Test Data Requirements
Note on D5: Follow the suggested steps to ensure that the coverage you are developing adequately adresses the business needs of the project. Your discoveries in this area will need to be vetted by the various stakeholders on the project. Helps answer the question, "How do I know that I am testing the right stuff?"
Note on F6: 1. Discover and read available documentation on the areas to be tested. 2. Identify areas where you have questions. 3. Interview appropriate stakeholders to help clarify your understanding of the areas you are analyzing. Keep in mind that your view and that of the stakeholder may not match initially. 4. Create a tool/spreadsheet/flow chart to help you visualize the project as you understand it. a. Start with core functionality and add additional components as you learn more. b. Check with Busines Analysts, development or architechture groups as they likely have created documents to help you in this task. 5. Create a traceability matrix between known requirements and your developing test plan/strategy. This matrix will initially only have requirements. Later, as test cases are developed, they can be assigned to the appropriate requirement. Include some type of prioritization to the requirements to help you make informed decisions when testcase development and testing begins. Priorities can be based on things like: a. Business needs b. Stakeholder concerns c. Complexity of specific requirements d. Newness of requirements e. Customer needs f. Known trouble spots g. Always be looking for 'hidden' requirements that are not explicity stated (implied).
Note on F25: Understand your test data requirements. In today's ever changing environment of interconnected devices and applications, it is critical to have a solid understanding of how data is shared. Part of any good overall test strategy is a comprehensive view of the data needs of the system to be tested. This means having a view from functional, integration, use case and other areas such as performance. Estimate the test data requirements for the total effort. This can be very complex. Reusability where possible is very important. Some of the data you need may already exist. Try to add and modify any existing data where possible. Be sure to get help with your initial estimates. Don't forget to include data for integrated applications in your estimates. Keep in mind, that the integrated component test groups may have data that you can use.

## Assessment Steps
Task Name |  |  | Back to TOC
Analysis/Research_2
Assessment Steps
Impact/Risk Assessment
Complete the Picture of the Software to be Tested
Note on E7: Perform a preliminary Impact/Risk Assessment to identify any unusual project aspects that may require non-standard test strategies or may pose a risk to the project schedule. The documents you read and interviews with stakeholders will help you in this area.
Note on H7: Suggestions: 1. Extremely complex components 2. Modules known to have high defect rates 3. Complex data integration requirements 4. Version control issues when integrated components are changing whilke your software is under test. 5. Untried new architecture or communication methodologies. 6. Extreme delivery time frames. 7. Extreme test data requirements - for example, certain modules such as reports can require large volumes of data. 8. Demanding stakeholders. 9. Timely availability of test environments. 10. Test scheduling conflicts with intergrated application teams. 11. Large integration components requiring scheduling cooperation with multiple outside development groups. 12. Vendor support issues. 13. Staffing/resource limitations. 14. Scope creep - probably the worst of all. Ask you mentor to explain. 15. Etc., Etc.
Note on H25: Continue building out you mental pictue of the software components/relationships to be tested. Don't forget data sharing relationships: 1. Core Components (use the 80/20 rule) 80% of the product's use will usually be in 20% of the modules to be tested. Start here if you can. These will likely be the first developed. 2. Secondary components - the other 80%. Use your priorities list. 3. Integrated Components. Look for general communication and data sharing in things like reports and primary record areas. 4. Determine the order that development will be releasing the modules. This may depend on what type of shop you work in; full agile, hybrid agile, waterfall or something else. 5. Evaluate what you can see at this point and begin piecing together your best stategy fit. Remember that your strategy will consist of many different parts depending on what you analysis reveals.

## Strategy_Component_Overview_1
Here are some of the basic strategy approaches that can be combined into your overall test strategy. This list is just a general example to help get you pointed in the right direction. Your shop may have additional or different things on this list.
Back to TOC
1 | Functional Testing
Everything
Core Only
Specific Modules
Business Priority
2 | Integration Testing
All
Core Only
Specific Modules
3 | Regression
Manually Executed
Automated
Combination/All
Specific Modules
Core
Business Priority
4 | Performance Testing
Ususally done by a specialist group - identify them
5 | Smoke Acceptance Testing
Usually done between releases or test cycles - typically used as an entrance criteria to the test phase
6 | System/End to End Testing
In some shops, these are the same. In others, different. This can be used as a broader version of acceptance
testing to provide a more 'in depth' look at the software's stability. Business 'Use Cases' can be applied in this area.

## Strategy_Component_Overview_2
Basic strategy approaches (continued)
Back to TOC
7 | Test Tools
Automation
Tool Type
In-House
Off Shore- Third Party-Consultant
Manual Testing
Combination
8 | Test Environment Requirements - Usually specified by the Development Group
Hardware
Software Systems
Specify what specific environment resources your strategy expects to be available.
9 | Test Data Creation
Use/Modify existing data - either yours or your partner's application data
Create New Data
Combination of new and reused data
Specify the particular data types that your strategy will require.
Where possible, specify 'how much' of each data type will be required. 10 records? 10,000 records?
10 | Test Result Reporting
What data will be reported
How will it be reported
How often will it be reported
To whom will it be reported
11 | Testing Timeframes
Length of each cycle/iteration
How many cycles per release
How many days per/cycle
Length of project - rough estimate
Total cycles/releases
Man Days per/cycle
Calendar
12 | Risks and Mitigation
Listing of key risks to the project
Resources
Data Development
Test environment availability
Time Frames
Vendor Support
Etc.
Risk Mitigation
What strategies do you recommend if any of the items in your impact/risk analysis
turn out to be problems?
13 | Responsibilities | Who is responsible for each part of the strategy.

## In Closing
In Closing | Back to TOC
This template concerns the ‘analytical process’ as it relates to the software test engineer and their effort to create a satisfactory test strategy for a project. You can imagine how difficult this can be in today’s development world. Consideration of issues such as test data and test environment creation along with the related automation concerns are part of what this template is about. The purpose of this is to help train the test engineer how to think about their project. How to determine what is important, what is less so, and to identify places where things might get overlooked. I think that most software project managers would agree that good analysis is critical in providing the desired quality end product. Analysis continues throughout the SDLC, whatever that may mean for a specific project. In today’s Agile/Iterative development world, the "small piece" approach to the iterative development process still requires good analysis. I would suggest that analysis is even more important due to all the moving parts and unknowns inherent in iterative methodologies. When I refer to analysis ability, I refer to the ability of the test engineer to be able to see the larger test strategy picture through the haze of iteration because they have been trained in what to look for. This, ultimately, helps both the test engineer and the project. Certainly, this template is not all inclusive nor does it contain any new earth-shattering concepts. What it tries to do, is to define a basic framework for the uninitiated test engineer to follow. Hopefully, this will lead to more robust and inclusive test strategies and fewer critical oversights. I strongly suggest that a mentor work with the new test engineer when using this template. If you have any questions or suggestions, feel free to let me know at ckam888@aol.com. Please put Analysis Template in the header.